## 17.12.2015
Modules in Front-End
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Critical | High | Medium | Low | Automated | Manual
Навигация | 0 | 10 | 0 | 0 | 0 | 24 | 0 | 24 | 0
Мой Курсове | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 8 | 0
Архив | 0 | 0 | 2 | 0 | 0 | 6 | 0 | 6 | 0
Total | 0 | 12 | 2 | 0 | 0 | 38 | 0 | 38 | 0
Modules in Administrator Part
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Critical | High | Medium | Low | Automated | Manual
Курсове и лекции | 5 | 7 | 4 | 4 | 5 | 14 | 6 | 13 | 1
Категории курсове | 7 | 9 | 3 | 4 | 2 | 16 | 3 | 15 | 1
Категории - йерархия | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
Студенти в курсове | 6 | 10 | 6 | 4 | 0 | 26 | 2 | 24 | 1
Групи | 0 | 2 | 11 | 0 | 3 | 10 | 3 | 10 | 0
Домашно | 6 | 6 | 5 | 4 | 7 | 21 | 3 | 18 | 2
Курсове, инстанции и лекции | 24 | 18 | 13 | 10 | 0 | 56 | 3 | 63 | 2
Единични курсове (Детска академия) | 0 | 23 | 5 | 0 | 0 | 26 | 11 | 15 | 2
Лицензи | 1 | 15 | 1 | 0 | 0 | 17 | 2 | 15 | 1
Статистики за студентите | 0 | 4 | 1 | 0 | 3 | 5 | 0 | 5 | 0
Статистика за студентите по години | 0 | 0 | 8 | 0 | 3 | 8 | 0 | 8 | 0
Анкети за курсове | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Статистика анкети за курсове | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0
Отписани студенти от курсове | 0 | 11 | 0 | 0 | 0 | 11 | 3 | 8 | 2
Total | 50 | 105 | 59 | 26 | 23 | 213 | 36 | 197 | 12
Total
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Critical | High | Medium | Low | Automated | Manual
Total | 50 | 117 | 71 | 28 | 23 | 251 | 36 | 235 | 28
Auto/Manual Tests Statistic | Cases (count) | Cases % | Automated (count) | Automated % | Manual (count) | Manual %
Front-End | 14 | 5.5118 | 0 | 0 | 38 | 15.1394
Admin | 240 | 94.4882 | 23 | 100 | 213 | 84.8606
All | 254 | 100 | 23 | 100 | 251 | 100
Priority Cases Statistic | Critical (count) | Critical % | High (count) | High % | Middle (count) | Middle % | Low (count) | Low %
Front-End | 0 | 0 | 12 | 10.2564 | 2 | 3.2787 | 0 | 0
Admin | 50 | 100 | 105 | 89.7436 | 59 | 96.7213 | 26 | 100
All | 50 | 100 | 117 | 100 | 61 | 100 | 26 | 100
Bugs by status | In Progress | Done
Front-End | 0 | 0
Administrator part | 21 | 4
Active bugs | Critical | High | Medium | Low | All
User part | 0 | 0 |  | 0 | 0
Administrator part | 1 | 4 | 3 | 4 | 12
All | 1 | 4 | 3 | 4 | 12
Active bugs by severity
Critical | 1
High | 4
Medium | 3
Low | 4

## 08.01.2016
Modules in Front-End
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Very High | High | Medium | Low | Automated | Manual
Навигация | 0 | 10 | 0 | 0 | 0 | 24 | 0 | 24 | 0
Мой Курсове | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 8 | 0
Архив | 0 | 0 | 2 | 0 | 0 | 6 | 0 | 6 | 0
Total | 0 | 12 | 2 | 0 | 0 | 38 | 0 | 38 | 0
Modules in Administrator Part
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Very High | High | Medium | Low | Automated | Manual
Курсове и лекции | 5 | 7 | 4 | 4 | 16 | 4 | 3 | 17 | 3
Категории курсове | 7 | 9 | 3 | 4 | 18 | 0 | 3 | 15 | 3
Категории - йерархия | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
Студенти в курсове | 7 | 10 | 6 | 4 | 12 | 15 | 1 | 26 | 1
Групи | 0 | 2 | 11 | 0 | 0 | 13 | 3 | 10 | 0
Домашно | 6 | 6 | 5 | 4 | 0 | 21 | 3 | 18 | 2
Курсове, инстанции и лекции | 24 | 18 | 13 | 10 | 10 | 46 | 3 | 63 | 2
Детска Академия | 24 | 4 | 3 | 0 | 3 | 27 | 7 | 23 | 6
Лицензи | 1 | 15 | 1 | 0 | 0 | 17 | 2 | 15 | 2
Статистики за студентите | 0 | 4 | 1 | 0 | 0 | 5 | 0 | 5 | 0
Статистика за студентите по години | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 0
Анкети за курсове | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Статистика анкети за курсове | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0
Отписани студенти от курсове | 0 | 11 | 0 | 0 | 0 | 11 | 3 | 8 | 2
Total | 75 | 86 | 57 | 26 | 60 | 169 | 28 | 211 | 21
Total
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Critical | High | Medium | Low | Automated | Manual
Total | 75 | 98 | 69 | 28 | 60 | 207 | 28 | 249 | 28
Auto/Manual Tests Statistic | Cases (count) | Cases % | Automated (count) | Automated % | Manual (count) | Manual %
Front-End | 14 | 5.4264 | 0 | 0 | 38 | 18.3575
Admin | 244 | 94.5736 | 60 | 100 | 169 | 81.6425
All | 258 | 100 | 60 | 100 | 207 | 100
Priority Cases Statistic | Critical (count) | Critical % | High (count) | High % | Middle (count) | Middle % | Low (count) | Low %
Front-End | 0 | 0 | 12 | 12.2449 | 2 | 3.3898 | 0 | 0
Admin | 75 | 100 | 86 | 87.7551 | 57 | 96.6102 | 26 | 100
All | 75 | 100 | 98 | 100 | 59 | 100 | 26 | 100
Bugs by status | In Progress | Done
Front-End | 0 | 0
Administrator part | 21 | 4
Active bugs | Critical | High | Medium | Low | All
User part | 0 | 0 | 0 | 0 | 0
Administrator part | 6 | 5 | 7 | 3 | 21
All | 6 | 5 | 7 | 3 | 21
Active bugs by severity
Critical | 6
High | 5
Medium | 7
Low | 3

## 15.01.2016
Modules in Front-End
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Very High | High | Medium | Low | Automated | Manual
Навигация | 0 | 10 | 0 | 0 | 0 | 24 | 0 | 24 | 0
Мой Курсове | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 8 | 0
Архив | 0 | 0 | 2 | 0 | 0 | 6 | 0 | 6 | 0
Total | 0 | 12 | 2 | 0 | 0 | 38 | 0 | 38 | 0
Modules in Administrator Part
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Very High | High | Medium | Low | Automated | Manual
Курсове и лекции | 18 | 22 | 4 | 4 | 41 | 7 | 5 | 43 | 5
Категории курсове | 7 | 9 | 3 | 4 | 12 | 0 | 1 | 11 | 3
Категории - йерархия | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
Студенти в курсове | 6 | 15 | 6 | 5 | 19 | 13 | 1 | 31 | 1
Групи | 1 | 2 | 11 | 0 | 13 | 1 | 3 | 11 | 0
Домашно | 6 | 6 | 5 | 4 | 12 | 9 | 4 | 17 | 4
Курсове, инстанции и лекции | 24 | 18 | 13 | 10 | 18 | 40 | 3 | 55 | 2
Детска Академия | 34 | 26 | 3 | 0 | 38 | 25 | 10 | 53 | 8
Лицензи | 1 | 15 | 1 | 0 | 5 | 12 | 0 | 17 | 0
Статистики за студентите | 0 | 2 | 5 | 0 | 7 | 0 | 3 | 4 | 3
Статистика за студентите по години | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 0
Анкети за курсове | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Статистика анкети за курсове | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0
Отписани студенти от курсове | 0 | 10 | 3 | 0 | 13 | 0 | 9 | 4 | 3
Total | 98 | 125 | 64 | 27 | 179 | 117 | 39 | 257 | 29
Total
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Critical | High | Medium | Low | Automated | Manual
Total | 98 | 137 | 76 | 29 | 179 | 155 | 39 | 295 | 28
Auto/Manual Tests Statistic | Cases (count) | Cases % | Automated (count) | Automated % | Manual (count) | Manual %
Front-End | 14 | 4.2683 | 0 | 0 | 38 | 24.5161
Admin | 314 | 95.7317 | 179 | 100 | 117 | 75.4839
All | 328 | 100 | 179 | 100 | 155 | 100
Priority Cases Statistic | Critical (count) | Critical % | High (count) | High % | Middle (count) | Middle % | Low (count) | Low %
Front-End | 0 | 0 | 12 | 8.7591 | 2 | 3.0303 | 0 | 0
Admin | 98 | 100 | 125 | 91.2409 | 64 | 96.9697 | 27 | 100
All | 98 | 100 | 137 | 100 | 66 | 100 | 27 | 100
Bugs by status | In Progress | Done
Front-End | 0 | 0
Administrator part | 21 | 4
Active bugs | Critical | High | Medium | Low | All
User part | 0 | 0 | 0 | 0 | 0
Administrator part | 5 | 10 | 10 | 3 | 28
All | 5 | 10 | 10 | 3 | 28
Active bugs by severity
Critical | 5
High | 10
Medium | 10
Low | 3

## 22.01.2016
Modules in Front-End
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Very High | High | Medium | Low | Automated | Manual
Навигация | 0 | 10 | 0 | 0 | 4 | 0 | 0 | 4 | 0
Мой Курсове | 0 | 2 | 0 | 0 | 5 | 3 | 0 | 8 | 0
Архив | 0 | 0 | 2 | 0 | 0 | 6 | 6 | 0 | 0
Total | 0 | 12 | 2 | 0 | 9 | 9 | 6 | 12 | 0
Modules in Administrator Part
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| Very High | High | Medium | Low | Automated | Manual
Курсове и лекции | 18 | 22 | 4 | 4 | 41 | 7 | 42 | 1 | 6
Категории курсове | 7 | 9 | 3 | 4 | 12 | 0 | 1 | 11 | 3
Категории - йерархия | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
Студенти в курсове | 6 | 15 | 6 | 5 | 19 | 13 | 1 | 31 | 1
Групи | 1 | 2 | 11 | 0 | 13 | 1 | 3 | 11 | 0
Домашно | 6 | 6 | 5 | 4 | 12 | 9 | 4 | 17 | 4
Курсове, инстанции и лекции | 24 | 18 | 13 | 10 | 33 | 25 | 3 | 60 | 2
Детска Академия | 34 | 26 | 3 | 0 | 38 | 25 | 10 | 53 | 8
Лицензи | 1 | 15 | 1 | 0 | 5 | 12 | 0 | 17 | 0
Статистики за студентите | 0 | 2 | 5 | 0 | 7 | 0 | 3 | 4 | 3
Статистика за студентите по години | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 12 | 0
Анкети за курсове | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Статистика анкети за курсове | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0
Отписани студенти от курсове | 0 | 10 | 3 | 0 | 13 | 0 | 9 | 4 | 3
Total | 98 | 125 | 68 | 27 | 194 | 106 | 76 | 224 | 30
Total
Module | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass
| VeryHigh | High | Medium | Low | Automated | Manual
Total | 98 | 137 | 80 | 29 | 203 | 115 | 82 | 236 | 28
Auto/Manual Tests Statistic | Cases (count) | Cases % | Automated (count) | Automated % | Manual (count) | Manual %
Front-End | 14 | 4.2169 | 9 | 4.4335 | 9 | 7.8261
Admin | 318 | 95.7831 | 194 | 95.5665 | 106 | 92.1739
All | 332 | 100 | 203 | 100 | 115 | 100
Priority Cases Statistic | Critical (count) | Critical % | High (count) | High % | Middle (count) | Middle % | Low (count) | Low %
Front-End | 0 | 0 | 12 | 8.7591 | 2 | 2.8571 | 0 | 0
Admin | 98 | 100 | 125 | 91.2409 | 68 | 97.1429 | 27 | 100
All | 98 | 100 | 137 | 100 | 70 | 100 | 27 | 100
Bugs by status | In Progress | Done
Front-End | 0 | 0
Administrator part | 20 | 5
Active bugs | Critical | High | Medium | Low | All
User part | 0 | 0 | 0 | 0 | 0
Administrator part | 7 | 10 | 10 | 3 | 30
All | 6 | 10 | 10 | 3 | 30
Active bugs by severity
Critical | 6
High | 10
Medium | 10
Low | 3

## Compare
TOTAL | [9 empty] | Difference Between Third and Forth
Week | Cases |  |  |  | Tests |  |  |  | Bugs found | Week | Cases |  |  |  | Tests |  |  |  | Bugs found
| Priority |  |  |  | Testing |  | Fail | Pass |  |  | Priority |  |  |  | Testing |  | Fail | Pass
| Critical | High | Medium | Low | Automated | Manual |  |  |  |  | Critical | High | Medium | Low | Automated | Manual
First | 50 | 117 | 71 | 28 | 23 | 251 | 36 | 235 | 12 | Third | 98 | 137 | 76 | 29 | 179 | 155 | 39 | 295 | 28
Second | 75 | 98 | 69 | 28 | 60 | 207 | 28 | 249 | 21 | Forth | 98 | 137 | 80 | 29 | 203 | 115 | 45 | 279 | 29
Third | 98 | 137 | 76 | 29 | 179 | 155 | 39 | 295 | 28 | Difference | 0 | 0 | 4 | 0 | 24 | -40 | 6 | -16 | 1
Forth | 98 | 137 | 80 | 29 | 203 | 115 | 45 | 279 | 29