## Sheet1
Organize a Company Anniversary Party
| Story | Task | Priority | Estimate
1 | Allocate budget |  | 1 | 0
1.1 |  | Prepare budget report | 1
1.2 |  | Update report | 2
2 | Ball Hall |  | 1 | 0
2.1 |  | Find a hall with a big enough table for ~40 people and space for dance | 1
2.2 |  | Negotiate price | 1
3 | Guests List and Mails |  | 1 | 0
3.1 |  | Create list with current employees | 1
3.2 |  | Create list with all former employees | 1
3.3 |  | Create list with all former employees | 1
|  | Send invitation e-mails to all guests | 2
4 | Food and Drink |  | 1 | 0
4.1 |  | Hire a food delivery company | 1
4.2 |  | Hire a food delivery company | 1
4.3 |  | Hire a soft drinks delivery company | 1
5 | Presents |  | 2 | 0
5.1 |  | Buy a box of chocolates for each guest | 2
5.2 |  | Buy an alcohol bottle for each guest | 2
5.3 |  | Order a souvenir for each guest with company logo | 2
5.4 |  | Make a gift package for the presents of each guest | 2
6 | Hotel |  | 3 | 0
6.1 |  | Check for confirmed guests | 3
6.2 |  | Book rooms for guests | 3
6.3 |  | Inform guests | 3
7 | Music |  | 3 | 0
7.1 |  | Hire a DJ | 3
7.2 |  | Hire Milko Kalaidjiev | 3
7.3 |  | Hire a gypsy orchestra | 3
7.4 |  | Hire a sound system | 3
8 | Photos |  | 3 | 0
8.1 |  | Hire a photographer | 3